## Consolidated
Team Member | Chris | Richard | Josh | Total
Tasks Estimations | 26.5 | 31.5 | 23.5 | 81.5

## Chris
| User Story | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7 | Task 8 | Task 9 | Task 10
Task | As a logged-in user, I want to search for specific meetings by typing in keywords into a search bar located on my home page such as the meeting’s date or using words/phrases that came up during the meeting, so that I can then access that meeting’s summary and details. If no meetings show up as a result of the search, then no saved meetings exist for the user or no meetings matching the search terms currently exist. | Task 1: Create a search bar on the home page for users to provide input to search for specified meeting; Task 2: Implement functionality for the user to search by date or keywords using the search bar; Task 3: Display search results in a list on a new page, and display the found meetings' basic information; Task 4: Add a link to each displayed meeting that lets the user navigate to the meeting's summary and details
Estimation (hours) | 13.5 | Task 1: 2.5; Task 2: 3; Task 3: 4; Task 4: 4
Task | As a logged in user I want to upload and store a video recording of a meeting in order to keep detailed records and rewatch recordings when needed. | Task 1: Create a button on the frontend in order to access user filesystem; Task 2: Send audio file to the backend. Store in DB for corresponding user; Task 3: Validate that the recordings uploaded are of a proper size, format, duration, etc.; Task 4: Display recorded video with the meeting in the meeting's summary and details page
Estimation (hours) | 13 | Task 1: 2; Task 2: 3; Task 3: 4; Task 4: 4

## Richard
| User Story | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7 | Task 8 | Task 9 | Task 10
Task | As a logged-in user, if you are looking for a meeting summary, you can navigate to the Meetings button in your user portal. If you need to get a summary for a new meeting, simply click the New Meeting button and upload the audio recording of your meeting. As the meeting transcript and summary load, you can see their progress in the dashboard. Once the meeting is loaded, click on it in the table that says Meetings. All of this is under the Meeting tab in the dashboard. Once you click on a meeting, you will be able to see and export the transcript and summary. | Task 1: Retrieve a list of all previous meetings from DB for a user; Task 2: Send audio file to assembly ai api to generate summary data; Task 3: Send and display meeting data to frontend; Task 4: Enable meetings on frontend to be clickable and reveal more meeting data; Task 5: Create dropdown or settings manager for user to choose what data to display
Estimation (hours) | 17.5 | Task 1: 3; Task 2: 2.5; Task 3: 4; Task 4: 4; Task 5: 4
Task | As a logged-out user, you can sign up by navigating to the Create an Account page and clicking on the Create Account button on the homepage. Once you click the Create Account button, you can create an account by either clicking the Signup with Google button or manually filling out the required fields for an account. After the account is created, you will be redirected to the dashboard, and your sign up will be complete. | Task 1: Create sign up/login page on the home page.; Task 2: Create forms and buttons for users to fill in account information (emails,password, etc.) for manual sign up/login on the sign up/login page; Task 3: Integrate Google OAuth for sign up and login; Task 4: Create functions necessary to keep track of new account information and send the information to the DB for the user; Task 5: Create a new user account in the database when the sign up form is successfully submitted
Estimation (hours) | 14 | Task 1: 2.5; Task 2: 2.5; Task 3: 3; Task 4: 3; Task 5: 3

## Josh
| User Story | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6 | Task 7 | Task 8 | Task 9 | Task 10
Task | As a logged in user, I want to delete a saved meeting on my account in order to remove error, duplicate, or unnecessary data to avoid confusion or free up storage space. | Task 1: Create a button on meeting summary page (frontend) to delete the corresponding meeting.; Task 2: Delete the corresponding files (audio recording, transcript, summary) from DB for the respective user's meeting (backend).; Task 3: Update the frontend to display "meeting has been deleted" message or similar notification.
Estimation (hours) | 7.5 | Task 1: 2; Task 2: 2.5; Task 3: 3
Task | As a logged in user, I want to update my account information (email, linked Google account, password, etc.) in order to keep my account secure or better reflect my currently used login information. As a logged in user, I can access my Account Information page by pressing the Account Information button in your home page. I will be directed to a page where I can change account fields such as my email or password by typing a new one in a text box underneath your current account info. I can confirm the changes by pressing the Confirm button at the bottom of the page. | Task 1: Create an account management page accessible from the user's homepage to access changing account information.; Task 2: Add a home page button that links to the account management page and add the link to the account management page on the site's navbar.; Task 3: Fetch the user's current account information from the database and display it on the account management page.; Task 4: Add input fields and forms where users can enter a new email address, password, etc., and allow the user to update linked Google account, also validate inputs for the forms; Task 5: Update the changed user account information in the database
Estimation (hours) | 16 | Task 1: 2.5; Task 2: 2.5; Task 3: 4; Task 4: 3; Task 5: 4